## RABillBrowse_projwise6381975259
Project RA Bill
01 Nyati Prosperity-2
Bill Date From 16/03/2023 To 16/05/2023
Page 1 of 1
Total Records: 7 Records 1 To 7
Project | WO NO | RA Bill | RA Bill Date | Contractor | Executed_By | Voucher_No | TASK | Labour_Name | Qty | Unit | Rate | PS % | Retention_Amt | WC_Amount | Tax_Scheme_Name | Tax Amount | Amount with Tax | Total Amount | Status | Credits | Debits | TDS_Amt
01 Nyati Prosperity-2 | 4 | 92202 | 10 May 2023 | Harish Contractor Pro | Harish Contractor Pro |  | Phase VI RCC Work - Pro | Labour Charges Pro | 5 | Sq.ft | 200 | 100 | 0 | 1000 | C + S GST 5% RD I/P | 50 | 1050 | 1050 | Unapproved | 0 | 0 | 0
A AMPLE TEST PROJECT | 5 | 92201 | 08 May 2023 | A&E Projects | A&E Projects | JV - 1637 | Footing PCC -M-10 | Laying PCC - 4" thk. | 0.05 | Sft. | 1234.56 | 100 | 0 | 61.73 | C + S GST 12% RD I/P | 7.4 | 69.13 | 69.13 | Approved | 0 | 0 | 1
A AMPLE TEST PROJECT | 32 | 92200 | 25 Apr 2023 | K.Muthukumaran | K.Muthukumaran | JV - 1633 | Survey Survey (Base line) | Survey (Basel ine) | 50 | R.S. | 100 | 100 | 250 | 5000 | C + S GST 18% RD/IP | 900 | 5900 | 5900 | Approved | 0 | 300 | 50
A AMPLE TEST PROJECT | 8 | 92196 | 11 Apr 2023 | 01 BMS Viswa Engineering Services Pvt .LTD | 01 BMS Viswa Engineering Services Pvt .LTD |  | Test Group Test 1 RCC Slab Work SQFT built area basis | RCC on Built-up Basis | 1 | Sq.ft | 2000 | 80 | 0 | 1600 | C + S GST 28% | 448 | 2048 | 2048 | Unapproved | 0 | 0 | 12
A SAMPLE PROJECT 3 | 172 | 4 | 21 Mar 2023 | A&E Projects | A&E Projects |  | Road Trimix Road (Lab) | Supply of Plastic Paper | 10 | Sft. | 121.22 | 100 | 60.61 | 1212.2 | C + S GST 12% I/P RCM | 145.46 | 1357.66 | 1357.66 | Unapproved | 0 | 0 | 0
A SAMPLE PROJECT 3 | 172 | 4 | 21 Mar 2023 | A&E Projects | A&E Projects |  | Road Trimix Road (Lab) | Supply of Plastic Paper | 24 | Sft. | 121.22 | 100 | 145.46 | 2909.28 | C + S GST 12% I/P RCM | 349.12 | 3258.4 | 3258.4 | Unapproved | 0 | 0 | 0
A SAMPLE PROJECT 3 | 172 | 4 | 21 Mar 2023 | A&E Projects | A&E Projects |  | Road Trimix Road (Lab) | Supply of Plastic Paper | 50 | Sft. | 121.22 | 100 | 303.05 | 6061 | C + S GST 12% I/P RCM | 727.32 | 6788.32 | 6788.32 | Unapproved | 0 | 0 | 0